## Timeline
Construction Project Timeline
By wordexceltemplates.com
ABC Construction Pvt. Ltd.
Project Name | Green Valley Housing Project |  |  | Start Date | 2026-01-01
Project Manager | Engr. Ali Raza |  |  | Expected End Date | 2026-06-30
Location | Faisalabad, Punjab |  |  | Prepared By | Planning & Scheduling Department
Data:
Task ID | Phase | Task Name | Start Date | End Date | Duration (Days) | Status | % Complete
T1 | Planning | Site Survey | 2026-01-01 | 2026-01-05 | 3 | Delayed | 25%
T2 | Planning | Design Approval | 2026-01-04 | 2026-01-10 | 5 | Delayed | 25%
T3 | Foundation | Excavation | 2026-01-11 | 2026-01-20 | 7 | Delayed | 25%
T4 | Foundation | Concrete Pouring | 2026-01-21 | 2026-01-30 | 8 | Delayed | 25%
T5 | Structure | Column Construction | 2026-02-01 | 2026-02-20 | 15 | Delayed | 25%
T6 | Structure | Slab Work | 2026-02-21 | 2026-03-10 | 12 | Delayed | 25%
T7 | Finishing | Plaster & Paint | 2026-03-11 | 2026-04-30 | 37 | Delayed | 25%
T8 | Finishing | Electrical & Plumbing | 2026-05-01 | 2026-05-31 | 21 | In Progress | 50%
T9 | Final Stage | Inspection & Handover | 2026-06-01 | 2026-06-30 | 22 | Not Started | 0%
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
[5 empty] | 0 |  | 0
Formulas:
Planning & Scheduling Department = NETWORKDAYS([Start Date],[Start Date])
Status = IF([Start Date]="","",IF(TODAY()<[Start Date],"Not Started",IF(TODAY()>[Start Date],"Delayed","In Progress")))