## Kitchen Remodel
Small Family Kitchen Design Planning Sheet
Personal / Project Information
Homeowner Name | Sarah Ahmed |  | Address | 12 Maple Street, Cityville
Contact Number | +1 234 567 890 |  | Email Address | sarah.ahmed@email.com
Project Name | Small Family Kitchen Remodel |  | Kitchen Dimensions | 12 ft × 10 ft
Project Start Date | 2026-01-15 |  | Project End Date | 2026-02-15
Designer / Contractor | Bright Homes Interiors |  | Notes/Special Requirements | Include child-friendly storage, efficient small-space layout
Kitchen Layout & Components
Component | Location | Dimensions | Quantity | Notes
Kitchen Counter | Wall A | 8 ft × 2 ft | 1 | Granite countertop
Upper Cabinets | Wall A | 3 ft × 2 ft | 4 | Include shelves for dishes
Lower Cabinets | Wall A | 3 ft × 2 ft | 3 | Soft-close drawers
Refrigerator | Corner | 3 ft × 3 ft | 1 | Energy-efficient model
Stove / Oven | Wall B | 3 ft × 2 ft | 1 | Gas stove
Sink | Wall A | 2 ft × 2 ft | 1 | Stainless steel
Dishwasher | Wall A | 2 ft × 2 ft | 1 | Integrated style
Appliances & Fixtures Budget
Item | Quantity | Unit Cost ($) | Total Cost ($) | Note
Refrigerator | 1 | 800 | 800
Stove / Oven | 1 | 500 | 500
Dishwasher | 1 | 400 | 400
Sink | 1 | 150 | 150
Kitchen Counter | 1 | 1200 | 1200
|  | Grand Total Budget: | 3050
Materials & Finishes
Material | Area / Quantity | Unit Cost ($) | Total Cost ($) | Notes
Floor Tiles | 120 sq.ft | 3 | 360 | Anti-slip
Backsplash | 40 sq.ft | 8 | 320 | Ceramic
Paint | 150 sq.ft | 1.5 | 225 | Washable, light color
Cabinet Handles | 10 pcs | 5 | 50 | Stainless steel
| Grand Total Materials Cost: |  | 955
Timeline & Project Phases
Phase | Start Date | End Date | Status | Notes
Demolition | 2026-01-15 | 2026-01-16 | Completed | Remove old cabinets
Electrical & Plumbing | 2026-01-18 | 2026-01-22 | In Progress | Install outlets & piping
Cabinet & Counter Installation | 2026-01-23 | 2026-01-30 | Pending | Align with layout plan
Appliance Installation | 2026-01-31 | 2026-02-01 | Pending | Test all appliances
Finishing & Painting | 2026-02-04 | 2026-02-10 | Pending | Ensure smooth finish
Final Inspection | 2026-02-11 | 2026-02-15 | Pending | Approve completion
Entries for Usage / Notes
Component | Issue / Observation | Action Required | Completed (Yes/No) | Note
Sink | Slight leak in faucet | Replace seal | No
Dishwasher | Not aligned | Re-adjust placement | No
Stove | Gas pipe connection checked | Safe to use | Yes
Summary:
Description
Total Appliances Cost | 3050 | Total Materials Cost | 955
Total Project Cost | 4005 | Total Timeline Duration (days) | 27 days